## Dev Tasks
CypherEdge - Development Tasks
Task | What We Need | Why
1. Update System S3 + CloudFront | Currently using GitHub releases. Need to move to S3 + CloudFront. S3 stores files, CloudFront distributes them globally. Both work together. Talked to an industry expert, he suggested this approach. | Updates will be faster and more reliable. Less support tickets. Costs around $15-20 per month. Takes 3 days to implement. Your call on whether to go ahead or not.
2. GitHub Actions Automate Builds | Automated build system. Tested in CypherSol, works fine. Need to roll out to other codebases. | Saves manual build time. Reduces code breaking issues. Suggest implementing across all codebases.
3. CypherX Accuracy Outlier Handling | CypherX handles most statements fine but some edge cases fail - regional banks, unusual formats. Need 1000-2000 outlier samples to improve the model. | Will reduce manual intervention and support overhead. Can handle more banks and expand reach. Still in discussion. Need your call on priority.
Summary: Task 2 - Rollout to other codebases Task 1 - S3 migration, 3 days work Task 3 - Need priority decision Need approval on 1 and 2, priority call on 3.